## Project Gantt
Project Phase | Scope | Migratable FTE | Learning Curve | TL/TM HC | Mngr. HC | Total wo/buffer | Total | Migration Key Steps - A view at expected critical outcomes, items and activities. | Calendar weeks | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20 | Wk21 | Wk22 | Wk23 | Wk24 | Wk25 | Wk26 | Wk27 | Wk28 | Wk29 | Wk30 | Wk31 | Wk32 | Wk33 | Wk34 | Wk35 | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52
[9 empty] | Timeline weeks | wk01 | wk02 | wk03 | wk04 | wk05 | wk06 | wk07 | wk08 | wk09 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42 | wk43 | wk44
Phase 1 | Project | 1 | 1 | 1 | 1 | 3 | 4
| Total | 1 | 1 | 1 | 1 | 3 | 4
Business Case (Memo)
FBP approval
Functional head approval
ELT approg
GSC Head -1 approval
Opportunity Assessment (Detailed task scoping)
PID Approval
Hiring Request approval
Resource mobilization
NEO + GSC L&D business & training stage
Knowledge Transfer Business + System Training sessions + Assessments
Volume Transfer/Ramp-up stage
Hypercare stage
Hypercare Exit Success Criteria Review
Migration Sign-off recommendation
Recommended soonest Capacity Release
PID approval
request window is first 15 days of the monht
reply period of that request: by end of the respective monht
create the hiring approval request: approved every two weeks of each month
workday requisition - that takes about a week
PROJECT TIMELINE - Mexico HUB
❶
Opportunity Assessment
❷
Resource Onboarding
❸
L&D training
❹
Knowledge Transfer
❺
Volume Ramp up
❻
Hypercare
Project Closure