# GSC Migration Roadmap Playbook Version 3.4 – Gate 0 to Gate 1 for development

Version 1.0 Date April 13th 2026

Classification Internal

Owner Migrations Team
Author: HJA036

## Lifecycle phases and decision gates

Gate exit occurs when exit criteria and evidence are complete in the tracker. 
No explicit approver is required.

#### Migration structure standard

G0 Initiation, Business Case and work placement

G1 Approvals governance

G2 GSC’s PID creation – monthly cycle

G3 Talent acquisition (Resource mobilization)
G4 Migration artifacts

G5 Onboarding and learning (GSC L&D)
G6 Knowledge transfer

G7 Volume ramp up
G8 Hypercare and sign-off
G9 Post sign-off effort recalculation

### Gate 0 Initiation, Business Case and work placement

## Gate Entry criteria: Initial assessment complete

User Input
The Source Team POC (Point of contact) starts the creation of a new Migration project from Area to GSC, these will be referred to as Source team and Target team. In the initial stage of this migration request/project creation the user is prompted with the details that will create the records of the migration, these will become the core of the database for that migration, this database is standardized for all projects. 

The inputs, these should be AI assisted, that are prompted from the user are:

## Project name

## Migration Type (Options: “1:1 Transfer”, “New/Additional work, tasks or activities”

## Region

## Area

## Product (Lead Logistics, Customs, Lanside Transportation, ground Freight, LCL, Ocean (OTCX), Ocean (OPS), E-commerce, Contract Logistics, Project Logistics, Air, Cold Chain, Depots, LTA, OTC, STP, ATR)

## Function (AIR, OCE, HBDS,

## Proposed Scope of the project: this is a high-level scope of the project something that states what are the processes that are being migrated, a general detail that speaks about the FTEs and Job Levels, the process they are doing, this is just something similar to a problem statement, it is a general description of what is meant to be migrated.

## (Optional) Risks, referring to the potential already identified risks of migration, what can go wrong basis on the know details, if there are challenges that are already expected, anything that needs to be considered for such.

## These will become the initial set of “Attributes” of the project, more “Attributes” will continue being added or created.

## Key activities/Tool throughput/Application system

The tool will use the above inputs, along with additional information defined per deliverable or action, to process data and generate outputs. For each step, the tool clearly defines what data is processed and what outputs are produced, whether internal or external. Based on the user inputs, the tool initiates a determination process consisting of a series of logical evaluations and estimations that result in specific determinations and decisions. Additional data will be leveraged at different steps of the process. This data may originate from existing databases embedded within the tool or from external systems connected to it. The specific data sources and usage will be defined and described at each step as required.

- “Project Attributes Database” (PAD) creation
Tool Functionality: Create the initial project record, which serves as the core foundation of the project database. All user inputs are captured as standardized “Attributes” and linked to a unique alphanumeric project identifier, this alphanumeric project identified will be labeled as “RFS”.
This RFS and all the “Attributes” will be added to the tool database.

- Right-Placement assessment
Tool Functionality: The tool will take the user input and use the work-placement criteria (also known as right-placement criteria) to issue the site recommendation for the process to be hosted (e.g. MAA; BOM; PUN; MNL; CGD; MEX, etc.). 
This will create the “Migration Target site” attribute, which will be added to the PAD.

- Service Catalogue Review and Comparison against the “Detailed Scoping Document (task-level Opportunity Assessment)”
Tool Functionality: The tool prompts the user to complete the Detailed Scoping Document Task level Opportunity Assessment through a dedicated user interface. This document captures the full scope of the migration at task level, including all activities to be migrated and their alignment to the Maersk process taxonomy.

As it gets filled in, the tool compares each task against the relevant product level service catalogues stored within the tool database. Using AI enabled matching and direct comparison, the tool identifies tasks that are already covered by existing service catalogues and those that are not.

Tasks found in the service catalogues are automatically approved for migration. Tasks not found trigger a separate workflow, where the corresponding Functional Process Owner is notified. The Functional Process Owner is provided with access to the project space to review the tasks directly within the Detailed Scoping Document and decide whether each task is approved for GSC delivery and added to the service catalogue or rejected and removed from the migration scope.

The Detailed Scoping Document can be saved as work in progress or marked as completed by the user. Once completed, it becomes a project attribute which will be added to the PAD and is formally classified as a Migration Artifact.
The Detailed Scoping Document task level Opportunity Assessment also includes FTE calculations at task level. As a result, it produces a validated total FTE figure for the migration. If this value differs from the FTE number initially provided by the user in the project attributes, the tool will prompt the user to review and update the value accordingly.

If the user is not ready to complete the scoping exercise, this step may be paused. In such cases, the service catalogue review is also paused, and the user is prompted to complete the scoping exercise as soon as possible. The tool will display a disclaimer informing the user that while the process may continue toward “Gate 1 Approvals Governance”, any subsequent changes to scope or FTE outcomes resulting from the completed scoping exercise may require previously obtained approvals to be revisited and reconfirmed.

- Benefit calculation
Tool Functionality: Automatic cost calculation is performed based on user inputs, using the cost calculation model maintained by the BPM team. In addition, a separate travel cost calculator is applied. By default, travel costs for one resource are automatically included, assuming travel from the source team location to the target team location for training purposes, unless explicitly excluded by the user.

The tool also prompts the user to confirm whether severance costs apply to impacted resources. If applicable, severance values are automatically populated for each affected headcount as part of the cost calculation model. If severance data is not available within the tool, the user is required to validate the costs with the relevant FBP and manually input the confirmed values.

In addition, the tool automatically includes four months of dual run costs. These are calculated based on the project creation date and the system derived projected hiring start date, using the underlying logic and databases that support this process within the tool.

The resulting benefit calculation is recorded both as a migration attribute and as a formal migration artifact and is stored in the tool database.

- Project Gantt
Tool Functionality: The tool automatically starts the migration timeline upon project creation. It captures the project start date and generates the initial project Gantt. Based on the project creation date and system derived projected stage durations, the tool calculates the timelines for subsequent migration stages in weekly format, using the underlying logic and databases embedded within the tool. This gives as an output a timeline of the project that will be visible in the project status dashboard.

- Business case Document
Tool Functionality: Using the Project Attributes Database PAD, the Right Placement assessment output, the benefit calculation and the project Gantt the tool generates a draft business case for the user to review. This Business case is created basis the system derived Business case structure, using the underlying logic and databases that support this process within the tool. The business case is editable and once approved it is formally finalized. The approved business case is recorded both as a migration attribute and as a formal migration artifact and is stored in the tool database.

- Area PID to be released 
Tool Functionality: The user is prompted to identify and record the PIDs that will be released as part of the migration. This step applies only to 11 migrations. For new or additional work migrations, this input is not required. The user completes the defined fields requested by the tool. The resulting PID information is recorded both as a migration attribute and as a formal migration artifact and is stored in the tool database.

- Project Status Dashboard

Tool Functionality: The tool creates/Enables the project Dashboard for this project, this becomes the front page of the tool when accessed to see the details of the record of this project, from there the status and migration artifacts can be navigated, This project status dashboard will track the main project milestones, deadlines and status in a single visual itemized dashboard, like a board where each item

### Gate 1 Approvals governance

## Input

Using the business case output from Gate 0, a condensed table that contains the details for this migration is created, this will be displayed to the stakeholders that will be provided with access to the project space to review the Business case directly and approve or reject the migration project.

Key activities/Tool throughput/Application system

- Secure FBP Cost Benefit and Transfer of budget approval

Tool Functionality: A workflow is triggered to notify the corresponding FBP that their approval is required and that upon approval the request will automatically proceed to the next approval level

  - The FBP is granted access to the project space to review the condensed business case table and the full business case and the Condensed Benefit Calculation.

  - The FBP can approve or reject the migration project benefit calculation and budget transfer confirmation directly within the tool. This confirmation represents not only an approval but also a formal commitment as the FBP is responsible for executing the budget transfer within their financial ownership.

  - If approved, the tool automatically triggers the next approval workflow and notifies the respective Area Functional Head approval

- Secure Area Functional Head approval
Tool Functionality: A workflow is triggered to notify the corresponding Functional Head that their approval is required and that upon approval the request will automatically proceed to the next approval level

  - The Functional Head is granted access to the project space to review the condensed business case table and the full business case

  - The Functional Head can approve or reject the migration project directly within the tool

  - If approved, the tool automatically triggers the next approval workflow and notifies the respective GAM ELT approver.

- Secure GAM ELT approval
Tool Functionality: A workflow is created to consolidate migration projects requiring approval by the GAM ELT on a weekly basis. Once the weekly submission deadline is reached the corresponding Functional Head is notified that the project has been submitted for GAM ELT review.

The GAM ELT approver is granted access to the project space to review a condensed view of the projects pending approval. This view includes only the minimum set of information required for executive assessment including a high level project summary and an overview of the expected savings.

The GAM ELT approver can approve or reject the migration project directly within the tool. If approved the tool automatically proceeds with the next approval or execution step as defined by the governance workflow.

- Secure GSC functional head approvals
Tool Functionality: A workflow is triggered to notify the corresponding GSC Functional Head that their approval is required and that upon approval the request will automatically proceed to the next approval level

  - The GSC Functional Head is granted access to the project space to review the condensed business case table and the full business case

  - The GSC Functional Head can approve or reject the migration project directly within the tool

  - If approved, the tool automatically triggers the next approval workflow which will connect with the BPM systems and interface to secure the PID approval creation, this forms part of the “Gate 2: GSC’s PID creation – monthly cycle”

The resulting Approvals, Approval status, Approval request date and Approval date information is recorded both as a migration attribute and as a formal migration artifact and is stored in the tool database.